## Slide 1: Where We're Focusing
OPS PRIORITIES
Top priorities, agreed as a team. Together, this is how we answer Play to Win's Delivery Excellence and Operational Review asks. We're tackling one epic at a time, starting with the Deal-to-Delivery Playbook, and moving to the next once it has real momentum.
TOP 4 PRIORITIES
Deal-to-Delivery Playbook
Work is sold in shapes we cannot staff or deliver.
Focus now
Accountability Framework
Define accountability for every project, with clear delivery roles, executive sponsorship, and regular reviews that highlight high risk projects.
Next
Leadership Dashboards
One leadership dashboard — shoring, chargeability, margin, capacity, forecast, rate cards, burn, and revenue recognition.
Next
Capacity Planning & Romulus
Closing the skills and bench visibility gap so we can staff ahead of demand.
Next
ALSO SHORT-TERM · OTHER INITIATIVES
DGS Leadership Transition
Naazneen departs 12/31 — two-phase effort to map dependencies, resolve Extentia's operating model, and set leadership coverage.
Focus now
Intake Updates
Upstream of Delivery Models — alias routing is live; SME case request tool and RACI updates underway to close adoption gaps.
In Motion
Ops Transformation: Rebuild Scoping & Staffing
Deliverables go in, and a timeline and staffing plan come out, with AI doing real work and learning from what we deliver.
Taking shape
Earlier Delivery & Talent in Pursuits
Bring SME expertise into upfront deal evaluation to lift our win rate on the deals we already capture.
Quick win
Source: All Hands slide 16 (first six); Delivery Excellence kickoff slide 4 (Ops Transformation, Earlier Delivery)

## Slide 2: How to fill this in
HOW TO USE THIS TEMPLATE
Every priority gets the same six slides. If you do not know something yet, leave the prompt in place. Blank is fine. Do not guess.
1. Divider
Put here
The name of the priority and who owns it.
Why it matters
Everyone knows whose job this is.
2. Exec summary
Put here
Goal, problem, what we are changing, what it unlocks, and one key takeaway.
Why it matters
If someone reads only one slide, this is it.
3. Why now
Put here
Why this one, and why it cannot wait. A bullet for each reason, then what we need.
Why it matters
Leaders back things that feel urgent and clear.
4. How we are going about it
Put here
The steps or stories, a timeline with real dates, who is on the team, and who we partner with.
Why it matters
Shows there is a plan and a date to hold us to.
5. The stories
Put here
Each story gets a short name and how we will know it worked. 1 to 5 stories. MVP first, then after the MVP.
Why it matters
A story is one thing we can finish. This is how we measure progress.
6. Update
Put here
What got done, what is next, and what is in our way or what we need from you.
Why it matters
It keeps everyone current and tells leaders how to help.
Need more detail on something? Add a supporting-detail slide from the four layouts at the end.

## Slide 3: Deal to Delivery Playbook
CRITICAL ENABLERS
Owner(s)
Missy Foristall, Chris McComas, Deana Derocha
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 4: Deal to Delivery Playbook: Context
CRITICAL ENABLERS
Owner(s)
Missy Foristall, Chris McComas, Deana Derocha
KEY TAKEAWAY
If we do nothing else, we must stop selling what we cannot properly deliver.
2026 GOAL
Align how we scope, execute, and set client expectations, so what we sell is what we deliver.
In practice: each deal is sold on a named delivery model, with contract, scope and billing matched to it, and delivery follows that same shape from qualification through staffing.
THE PROBLEM
Work is sold in shapes we cannot staff or deliver.
There is no standardized, named set of delivery models that is declared at the point of sale, carried into contracting, enforced at staffing and used for delivery.
The delivery approach is decided implicitly by whoever is making decisions at that moment, and it is often not understood until the symptoms are visible to the client or a pivot needs investment.
WHAT WE ARE CHANGING
Every engagement and every track gets a named delivery model from a small, standard set, declared before review and staffing.
No SOW is signed without a model name attached, and that name determines governance.
Four starting models
Fixed Constraint Delivery, Velocity Based Delivery, Outcomes Based Delivery, Retainer
MVP: three stories, all three must work together
Delivery Models, Contracts, Methodology Standards
WHAT THIS UNLOCKS
We stop agreeing to unfeasible combinations, like fixed-price with no scope control.
Our pricing tools reflect true deliverability, not just theoretical margin.
We guide clients into how we work instead of inheriting whatever mix they bring.
Beyond the MVP
Supported by AI: estimation, pricing, and staffing follow once the MVP is solid, and we move toward metered or token-based commercial pricing.
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 5: Why now
DEAL-TO-DELIVERY PLAYBOOK · CLICK-DOWN · THE PROBLEM
Owner(s)
Missy Foristall, Chris McComas, Deana Derocha
Why this one, first: of the four, this is the most urgent to solve. Work is being sold in shapes we cannot staff or deliver, and that's costing us today — not a future risk. It's also our clearest answer to Play to Win's Delivery Excellence ask.
What's happening today
There is no standardized, named set of delivery models, from which an individual or set of models is required to be declared at the point of sale, carried into contracting, enforced at staffing and used for delivery.
As a result, the delivery approach for any given engagement, or track within an engagement, is decided implicitly and independently by whoever happens to be making decisions at that moment (executives, Sales, CPs, Delivery leads, etc.), rather than through one shared educated decision.
When these implicit decisions disagree with the type of engagement or client expectation, often it is not fully understood until the symptoms are already visible to the client, or we are at a point that a pivot will require investment.
So we need
We need a small set of authorized delivery models
That align approach, contract, and methodology standards
Allowing us to improve how we solution, estimate, and deliver
Source: All Hands slides 18 and 23 · Delivery Excellence slides 6 and 11

## Slide 6: How we're going about it
DEAL-TO-DELIVERY PLAYBOOK · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
Missy Foristall, Chris McComas, Deana Derocha
Every engagement, and every track within a multi-track program, must have an explicitly named delivery model (chosen from a small, standard set) declared before review, staffing, etc. and checked at fixed intervals afterward. The model determines governance, staffing, and authority; it is not inferred after the fact by whoever is doing the work.
Step 1
Delivery Models
Every deal categorized at qualification into one of 5-6 core models, so pricing and staffing follow a known shape.
Step 2
Contracts
Terms, scope language, and billing matched to the chosen model — no more fixed price with no scope control.
Step 3
Methodology Standards
Clear working practices, so we guide clients into how we work instead of inheriting whatever mix they bring.
Step 4
After the MVP
Supported by AI: Estimation, Pricing, and Staffing follow once the MVP is solid.
Oct 16th
Draft Models Gathered
Week of Oct. 26th
Base Model rationalization across groups
Oct 23rd Shifting to Nov 6th
Initial Models Well Defined
Will include iterative reviews with department leads and defined SMEs
Nov 13th
1st Batch of Models & Program "Stack" Guidance
This will be delivered in an agile manner getting quick guidance out in Q4 and iteratively fleshed out and evolved with feedback loops to drive improvements
The target
MVP done
[Date we are shooting for.]
Team
John
Chris
Partners
BU COOs
Delivery Leads
Enterprise Project Management
Client & Commercial teams
Finance
Source: All Hands slides 19, 21, 23 · Play to Win update (John and Chris) · Delivery Excellence slides 7, 9, 11

## Slide 7: The stories
DEAL-TO-DELIVERY PLAYBOOK · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
Missy Foristall, Chris McComas, Deana Derocha
Story
How we measure success
Status
The MVP
1
Delivery Models
[How will we know it worked? A number or a clear yes or no.]
[Status]
2
Contracts
[How will we know it worked? A number or a clear yes or no.]
[Status]
3
Methodology Standards
[How will we know it worked? A number or a clear yes or no.]
[Status]
After the MVP
4
Estimation
[How will we know it worked? A number or a clear yes or no.]
[Status]
5
Pricing
[How will we know it worked? A number or a clear yes or no.]
[Status]
6
Staffing
[How will we know it worked? A number or a clear yes or no.]
[Status]
Source: All Hands slide 23 (hidden) · Delivery Excellence slide 11 (hidden)

## Slide 8: Delivery Models: the four starting models
DEAL-TO-DELIVERY PLAYBOOK · DETAIL
Owner(s)
Missy Foristall, Chris McComas, Deana Derocha
MODEL 1
Fixed Constraint Delivery
A fixed constraint (budget, deadline, or scope) is set, and delivery is planned backward to it.
Key characteristics
Backcasted plan is mandatory before build starts — no backcast, no green light
Scope is fixed and baselined at Gate 1; change flows through CR (constraint-impacting) or Scope Bank (parity swaps)
Phase-gated structure with formal sign-offs
Squad Lead = Scrum Master
Success is binary at the end: did it ship, on time, in budget, to spec
MODEL 2
Velocity Based Delivery
A contracted team delivers at a predictable, measurable pace; value is demonstrated through throughput and periodic releases, not a fixed feature list.
Key characteristics
No fixed scope commitment — backlog is client-prioritized, reordered freely
Velocity baseline is established and defended
PI Planning cadence (8–10 weeks) anchors medium-term commitments
Squad Lead = Scrum Master
Contract states team capacity/pace is what's being bought — NOT a feature list
MODEL 3
Outcomes Based Delivery
A strategic product partnership; the backlog exists to move measurable business outcomes, not just to ship features.
Key characteristics
POD Led = Product Owner, with real authority — decision rights and roadmap access should be contractually explicit
Every backlog item is anchored to an OKR before it enters a sprint
Client Product Owner co-owns the roadmap (not just consulted)
Continuous discovery is a funded, scheduled activity
Quarterly roadmap/OKR review with Exec Sponsor
MODEL 4
Retainer(Site Support Example)
Live Ops/Support retainer running and sustaining what's already been built. This is not new development, this is protecting existing value and responding to it.
Key characteristics
Scope is reactive + scheduled maintenance
Governed by SLAs (response/resolution time by severity)
Staffing is typically lighter-weight and more specialized (support engineers, on-call rotation)
Escalation tiers are explicit (L1/L2/L3)
Requires a clear boundary between support and enhancement (CR)
Often runs alongside another model (e.g., Model 3 team drives new value while Model 4 team keeps the lights on)
Source: All Hands slide 20 · Delivery Excellence slide 8

## Slide 9: The recommendation: four rules
DEAL-TO-DELIVERY PLAYBOOK · DETAIL
Owner(s)
Missy Foristall, Chris McComas, Deana Derocha
Rule 1
Standardize a small set of named models mapped to commercial structure
No SOW is signed without a model name attached to it, and that name determines governance
(e.g., gates vs. PI cadence vs. OKR-anchored backlog)
Rule 2
Treat multi-track programs as portfolios of clearly defined tracks mapped to a model, not one label stretched over the whole account.
Program A:
Track A: Model 1 (backcasted platform build) +Track B: Model 3 (outcomes based page performance improvement )+
Track C: Model 2 (retainer - ops)
Rule 3
Require a kickoff certification.
A named accountable role (Program or Account Lead and Delivery Lead) signs off, at kickoff and at defined checkpoints, that the working model, the staffing, and the contract still agree with each other. Shift from "escalate when it's already broken" into "check before it can break."
Rule 4
Build leading indicators per model.
Make drift visible in week 2 to 4 of a track instead of at the next executive review.
Each model gets 3 to 4 checkable signals (e.g., for Model 1: is there a backcasted plan and is the client tracking to gates; for Model 2: is velocity being reported against contracted throughput)
Source: All Hands slide 19 · Delivery Excellence slide 7

## Slide 10: Deal to Delivery Playbook: Update
CRITICAL ENABLERS
Owner(s)
Missy Foristall, Chris McComas, Deana Derocha
WHAT HAS BEEN ACCOMPLISHED
Problem statement and recommendation drafted (Sept 16).
Four model examples defined (Sept 16).
Draft models gathered (Oct 16).
NEXT MILESTONES
Base Model rationalization across groups: week of Oct 26.
Initial Models Well Defined: Oct 23, shifting to Nov 6.
1st Batch of Models & Program "Stack" Guidance: Nov 13.
John and Chris are pulling together the problem statement, dependencies, size, and recommendation for the three MVP stories. We'll review what they bring back next time.
WHAT IS IN OUR WAY / WHAT WE NEED FROM YOU
Alignment on base model set (Delivery/Ops, Legal and Finance) and on model definition.
SME feedback, and intake routing.
Top risks: missed model(s) from the assessment, poor rollout and communication, and failure to use the models.
Everyone needs to lean in, support development of, and use these models. Participate, provide insights, give feedback, and embrace this initiative.
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 11: Accountability Framework
CRITICAL ENABLERS
Owner(s)
Missy Foristall, John Ewen
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 12: Accountability Framework: Context
CRITICAL ENABLERS
Owner(s)
Missy Foristall, John Ewen
KEY TAKEAWAY
Far too many key projects lack a shared understanding of who is accountable for the work that we do.
2026 GOAL
Codify and transform delivery leadership and accountability for every project, with clear delivery roles, executive sponsorship, and regular reviews that highlight high-risk projects.
In practice: every key project has named delivery roles and an executive sponsor, multitrack projects have agreed accountability, and quarterly reviews surface high-risk projects early.
THE PROBLEM
We are refining how we manage multitrack projects so project teams have precise leadership support, rather than running as one giant portfolio.
For multitrack and multi-Delivery Center projects, alignment needs to be agreed to and enforced.
This will inform everything from staffing to methodology to the role of escalation management and resolution.
WHAT WE ARE CHANGING
We will define accountability for every project.
We will establish the essential delivery roles needed and clarify existing roles to avoid overlap and gaps.
We are launching a workstream to define standard delivery roles and establish clear, supportive project-level structures across all major accounts.
Starting in Q4, we will establish a cadence of quarterly reviews. High risk projects will be highlighted in ongoing Delivery Excellence meetings.
WHAT THIS UNLOCKS
Delivery doesn't happen in a vacuum. Successes and escalations are tightly coupled with our Client Engagement model (Client Partners, Account Management) and Executive Sponsors.
Beyond the MVP
Expand quarterly reviews across the broader portfolio after the top 5 major clients per BU, and scale what works into methodology.
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 13: Why now
ACCOUNTABILITY FRAMEWORK · CLICK-DOWN · THE PROBLEM
Owner(s)
Missy Foristall, John Ewen
[Put here: one or two sentences on why this one, and why now. What does waiting cost us?]
What's happening today
To best support our integrated business units, we are refining how we manage accounts with multiple projects or multitrack projects to ensure project teams have precise leadership support, rather than running as one giant portfolio.
So we need
[Put here: what has to happen or be decided. One bullet per ask.]
[Why: this turns the worry into a clear ask.]
Source: All Hands slide 25 · Delivery Excellence slide 13

## Slide 14: How we're going about it
ACCOUNTABILITY FRAMEWORK · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
Missy Foristall, John Ewen
We are launching a workstream to define standard delivery roles and establish clear, supportive project-level structures across all major accounts.
Step 1
Accountability Clarified
We will define accountability for every project. For projects serviced by a single Delivery Center, this will be linear and familiar. For multitrack/multi-Delivery Center projects, alignment needs to be agreed to and enforced. This will inform everything from staffing to methodology to the role of escalation management and resolution.
Step 2
Defining Essential Roles
As new accountability models are defined, new roles may be necessary. We will establish the essential delivery roles needed to support this model and clarify existing roles to avoid overlap and gaps.
Step 3
Growth, Client Service and Executive Sponsorship
Delivery doesn’t happen in a vacuum. Successes and escalations will need to be tightly coupled with our Client Engagement model (Client Partners, Account Management) and Executive Sponsors. These partnerships will be evaluated for clarity, completeness and effectiveness with our modified delivery engine.
Step 4
Change Management will be Key
These changes will represent modifications to our ways of working and new standards which we will need to taught, supported and enforced. Training and continuous improvement will be key to helping the organization embrace new structures and ensure we learn from what works.
Step 5
Phased Rollout of Regular Reviews
Starting in Q4, we will establish a cadence of quarterly reviews to report on the accountability structure for multitrack programs. Each model will be assessed in terms of risk and opportunities for improvement. Additionally, high risk projects will be highlighted in ongoing Delivery Excellence meetings.
[Date]
[What is done by then]
[Date]
[What is done by then]
[Date]
[What is done by then]
[Date]
[What is done by then]
The target
MVP done
[Date we are shooting for.]
Team
BU COOs
Enterprise Project Management
Partners
[Who we work with]
[Who we work with]
Source: All Hands slide 25 · Delivery Excellence slide 13 (BU COOs and Enterprise Project Management co-lead)

## Slide 15: The stories
ACCOUNTABILITY FRAMEWORK · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
Missy Foristall, John Ewen
Story
How we measure success
Status
The MVP
1
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
2
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
3
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
After the MVP
4
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
5
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]

## Slide 16: Accountability Framework: Update
CRITICAL ENABLERS
Owner(s)
Missy Foristall, John Ewen
WHAT HAS BEEN ACCOMPLISHED
Workstream launching to define standard delivery roles and project-level structures across major accounts.
BU COOs and Enterprise Project Management are co-leading this initiative.
NEXT MILESTONES
Lock in the key accounts in each BU (top 5 major clients per BU): [enter date].
Define the required core roles for the Q4 launch: [enter date].
Start the quarterly reviews of the accountability structure for multitrack programs: Q4.
WHAT IS IN OUR WAY / WHAT WE NEED FROM YOU
Key accounts in each BU are not yet locked in, and core roles for the Q4 launch are not yet defined.
Change management will be key. These are modifications to our ways of working and new standards that we will need to teach, support, and enforce.
Training and continuous improvement will help the organization embrace new structures and ensure we learn from what works.
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 17: Leadership Dashboards
OPS PRIORITIES
Owner(s)
[Names]

## Slide 18: Leadership Dashboards
OPS PRIORITIES · EXEC SUMMARY
Owner(s)
[Names]
2026 Goal
[Put here: the one thing we want to be true by the end of 2026.]
[Why: everyone should know the finish line.]
The problem
We lack a singular place for leaders to go to see the health of their business.
Resource and financial data sit in separate systems, with no rate cards applied, no burn tracking, and no cross-BU revenue visibility (see Ugam/HelloWorld).
What we are changing
[Put here: what we will do differently. Use short bullets.]
[Why: it shows we have a plan, not just a worry.]
What this unlocks
[Put here: what gets better once this works.]
[Why: it is the reason the effort is worth it.]
Key takeaway
One Set of Numbers: One place to see the metrics that today live in too many reports — with AI doing the reconciliation, not a person.
Source: All Hands slide 27 · Delivery Excellence slide 15

## Slide 19: Why now
LEADERSHIP DASHBOARDS · CLICK-DOWN · THE PROBLEM
Owner(s)
[Names]
[Put here: one or two sentences on why this one, and why now. What does waiting cost us?]
What's happening today
We’re running the business off lagging metrics or incomplete ones. Example: We can see client or project margin but not practice margin. And costs live in a Finance spreadsheet that we see once a month.
So we need
One leadership dashboard, not just a data-reconciliation project.
It needs to show revenue, margin, and capacity forecasts, manage rate cards and actuals-for-burn, and tie revenue recognition to operational reporting, all in a single page view.
Source: All Hands slide 27 · Delivery Excellence slide 15

## Slide 20: How we're going about it
LEADERSHIP DASHBOARDS · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
[Put here: one line on how we are tackling this. The steps below fill in the detail.]
Step 1
Preliminary Thoughts
Dashboard of key metrics by BU (margin, revenue actuals compared to budget), top clients, average client margin, etc, that can be broken down by practice, L3, etc.
Will link out to existing reports for more details – no need to recreate the wheel for all metrics.
May need to be locked down to only key leaders based on what is included.
[Date]
[What is done by then]
[Date]
[What is done by then]
[Date]
[What is done by then]
The target
MVP done
[Date we are shooting for.]
Team
[Who does the work]
[Who does the work]
Partners
[Who we work with]
[Who we work with]
Source: All Hands slide 27 · Delivery Excellence slide 15

## Slide 21: The stories
LEADERSHIP DASHBOARDS · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
Story
How we measure success
Status
The MVP
1
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
2
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
3
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
After the MVP
4
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
5
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]

## Slide 22: Leadership Dashboards: Update
OPS PRIORITIES
Owner(s)
[Names]
What has been accomplished
[Put here: what got done since last time. Use dates, not "recently". Why: shows real progress.]
Next milestones
[Put here: what happens next, and by when. Why: people can hold us to it.]
What is in our way / what we need from you
[Put here: what is blocking us, and what we need from you. Say who, and by when. Why: this is how leaders can help.]

## Slide 23: Capacity Planning & Romulus
OPS PRIORITIES
Owner(s)
[Names]

## Slide 24: Capacity Planning & Romulus
OPS PRIORITIES · EXEC SUMMARY
Owner(s)
[Names]
2026 Goal
Move from insight to action: close the skills and bench visibility gap so we can staff ahead of demand.
The problem
[Put here: what is broken today, in plain words.]
[Why: people only back a fix if they can feel the problem.]
What we are changing
[Put here: what we will do differently. Use short bullets.]
[Why: it shows we have a plan, not just a worry.]
What this unlocks
[Put here: what gets better once this works.]
[Why: it is the reason the effort is worth it.]
Key takeaway
Next, we need further definition and to identify the dependencies that could block us. The three pillars are where our stories will come from, and we will shape them together with our other priorities (Leadership Dashboards, the Accountability Framework, the Deal-to-Delivery Playbook). Still coming, with more in the coming weeks.
Source: All Hands slide 29 · Delivery Excellence slide 26

## Slide 25: Why now
CAPACITY PLANNING & ROMULUS · CLICK-DOWN · THE PROBLEM
Owner(s)
[Names]
[Put here: one or two sentences on why this one, and why now. What does waiting cost us?]
What's happening today
[Put here: what is going on right now that makes this urgent. One bullet per point, add as many as you need.]
[Why: this is the reason to act now.]
So we need
[Put here: what has to happen or be decided. One bullet per ask.]
[Why: this turns the worry into a clear ask.]

## Slide 26: How we're going about it
CAPACITY PLANNING & ROMULUS · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
[Put here: one line on how we are tackling this. The steps below fill in the detail.]
Step 1
Pillar 1: Know who we have
We need skills captured in one place we can search, so we can find the right person for a role across practices. The outcome: one trusted view of skills instead of separate sources.
A skills data pilot with about 100 opt-in people from each of two teams, on a LinkedIn skills taxonomy. We still need to define what we need from it.
Step 2
Pillar 2: See what is coming
We need to review SF stages to see the pipeline earlier, so we can plan people around demand with RM pulled in earlier in the process, not at signature. The outcome: teams that are ready to start instead of scrambling after signing.
Smart Bench is a concept we are exploring. In plain terms: look ahead at what is likely to close, set clear rules for when we add or reduce capacity (hire, temporary help, or an outside partner), and plan how quickly people ramp on. What it means for us is still being defined.
Step 3
Pillar 3: One place to look
We need what we check today brought into one connected view, so we can move from insight to action with fewer places to look. The outcome: insight that points to the next move.
Today we check Salesforce, Workfront, pricing tools, spreadsheets, and SharePoint. Romulus is the tool we are building to help turn insight into action (next slide). It needs more feeding from the work in the other two pillars.
This year
We started with resource management, then stood up capacity planning.
Coming weeks
Like our other ops top priorities, we will build this out as an epic with stories underneath, so we can focus and prioritize.
Late October
FIRST FEATURES GO LIVE · FULL DEMO: Next Ops Town Hall
See the complete experience in action.
Next year
Capacity planning becomes how we run things and our priority focus for enhancement, with resource management as its child.
The target
MVP done
[Date we are shooting for.]
Team
[Who does the work]
[Who does the work]
Partners
[Who we work with]
[Who we work with]
Source: All Hands slides 29 and 33 · Delivery Excellence slide 26 (which says Mid-November, not Late October)

## Slide 27: The stories
CAPACITY PLANNING & ROMULUS · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
Story
How we measure success
Status
The stories
1
Pillar 1: Know who we have
We need skills captured in one place we can search, so we can find the right person for a role across practices.
[How will we know it worked? A number or a clear yes or no.]
Underway
2
Pillar 2: See what is coming
We need to review SF stages to see the pipeline earlier, so we can plan people around demand with RM pulled in earlier in the process, not at signature.
[How will we know it worked? A number or a clear yes or no.]
Exploring: Smart Bench
3
Pillar 3: One place to look
We need what we check today brought into one connected view, so we can move from insight to action with fewer places to look.
[How will we know it worked? A number or a clear yes or no.]
Being built: Romulus
Source: All Hands slide 29 · Delivery Excellence slide 26 (pillar 2 wording differs)

## Slide 28: Romulus
CAPACITY PLANNING & ROMULUS · SUPPORTING DETAIL
Owner(s)
[Names]
An operating system for resource management.
Romulus turns live demand, supply and financial data into a daily situation report — surfacing the staffing decisions a Resource Manager needs to make before they're asked. It's built to replace the spreadsheets, email chains, and tribal knowledge our business runs on today.
▲ This was the actual prompt that started it all ▲
Now here's the rest of the story…. In 3 minutes (or less)
Source: All Hands slide 32 · Delivery Excellence slide 28

## Slide 29: What you can do with it
CAPACITY PLANNING & ROMULUS · RELEASE MOMENTUM
Owner(s)
[Names]
1
See today’s situation
The morning briefing — overall health, the single most important finding, and the day’s top moves.
2
Suggest resources for open roles
Ranked candidates with fit rationale, availability, and recent project history.
3
Run what-if scenarios
Model a deal landing, a start date slipping, or filling from the bench — before committing.
4
Walk a decision through governance
Approval stages with policy checks surfaced at each gate. Full audit trail.
5
Ask in plain language
A conversational assistant grounded in current, real data — not general knowledge.
Source: All Hands slide 33 · Delivery Excellence slide 29

## Slide 30: Capacity Planning & Romulus: Update
OPS PRIORITIES
Owner(s)
[Names]
What has been accomplished
[Put here: what got done since last time. Use dates, not "recently". Why: shows real progress.]
Next milestones
[Put here: what happens next, and by when. Why: people can hold us to it.]
What is in our way / what we need from you
[Put here: what is blocking us, and what we need from you. Say who, and by when. Why: this is how leaders can help.]

## Slide 31: DGS Leadership Transition
OPS PRIORITIES
Owner(s)
[Names]

## Slide 32: DGS Leadership Transition
OPS PRIORITIES · EXEC SUMMARY
Owner(s)
[Names]
2026 Goal
[Put here: the one thing we want to be true by the end of 2026.]
[Why: everyone should know the finish line.]
The problem
[Put here: what is broken today, in plain words.]
[Why: people only back a fix if they can feel the problem.]
What we are changing
[Put here: what we will do differently. Use short bullets.]
[Why: it shows we have a plan, not just a worry.]
What this unlocks
[Put here: what gets better once this works.]
[Why: it is the reason the effort is worth it.]
Key takeaway
We have a hard deadline and a business with real complexity underneath it. This two-phase plan is how we capture the knowledge, resolve ownership, and land a clean transition by year-end.
Source: All Hands slide 35

## Slide 33: Why now
DGS LEADERSHIP TRANSITION · CLICK-DOWN · THE PROBLEM
Owner(s)
[Names]
Why this one, now: Naazneen's departure on 12/31 is a fixed deadline, and her role covers more ground than any one market realizes — global delivery, market relationships, capability development, and financial oversight. This is a two-phase effort to capture what she knows and put durable ownership in place before she leaves.
What's happening today
[Put here: what is going on right now that makes this urgent. One bullet per point, add as many as you need.]
[Why: this is the reason to act now.]
So we need
[Put here: what has to happen or be decided. One bullet per ask.]
[Why: this turns the worry into a clear ask.]
Source: All Hands slide 35

## Slide 34: How we're going about it
DGS LEADERSHIP TRANSITION · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
[Put here: one line on how we are tackling this. The steps below fill in the detail.]
Step 1
PHASE 1 · Intake, Validate, Plan · Sept 14 – Oct 16
Milestone: India trip Sept 25 – Oct 10 (AO)
Role & Org Mapping
Sessions with Naazneen's team to document formal and informal responsibilities, relationships, and escalation paths.
Coverage & Role Design
Determine who — and # of people — are needed to take on what Naazneen has been doing. Separate the DBT-specific work from the broader set of responsibilities she carries.
Alignment Prep
Establish scope, decision rights, and messaging ahead of wider stakeholder engagement.
Step 2
PHASE 2 · Align, Anchor, Execute · Oct 19 – Dec 20
Milestone: India trip mid-Nov (AO, Missy, Eric, McComas)
Operating Model Decisions
Finalize market vs. India ownership of delivery escalation, solutioning participation, and shared governance.
Leadership & Talent Plan
Confirm critical role coverage, succession, recruiting priorities, and capability gaps.
Execution & Handoff
Complete transition activities and communications ahead of the 12/31 departure.
Step 3
Extentia's Organic Revenue
Multi-market structure (US, ANZ, India, UK) and P&L ownership need to be resolved for 2027 — likely a longer runway than the core transition timeline. Tracking separately so it doesn't block Phase 1 & 2 progress.
Sept 14 – Oct 16
Phase 1: Intake, Validate, Plan
Milestone: India trip Sept 25 – Oct 10 (AO)
Oct 19 – Dec 20
Phase 2: Align, Anchor, Execute
Milestone: India trip mid-Nov (AO, Missy, Eric, McComas)
The target
12/31
Naazneen departs.
Team
[Who does the work]
[Who does the work]
Partners
[Who we work with]
[Who we work with]
Source: All Hands slide 35 and divider slide 34

## Slide 35: The stories
DGS LEADERSHIP TRANSITION · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
Story
How we measure success
Status
The MVP
1
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
2
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
3
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
After the MVP
4
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
5
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]

## Slide 36: DGS Leadership Transition
DGS LEADERSHIP TRANSITION · UNDERSTANDING NAAZNEEN’S ROLE AND PLANNING FOR THE FUTURE
Owner(s)
[Names]
Mapping Naazneen
Over the course of the trip I completed more than 30 intake interviews across DGS team members. We covered:
Our ways of working
How resources are identified
How the are trained and deployed
How the build their careers
Understanding how they support CXM
They view the US as a market, they don’t see the business units per se. Which lead to conversations around:
They other markets and how they operate.
Organic projects beyond the markets
How they create craft communities
An interim model
Naazneen’s departure creates a sizable hole in the business, but she has a good team of lieutenants.
An interim model leveraging her lieutenants has been identified
Ongoing interviews for Naaz’s backfill.
Could be sometime in Q1 before the role I filled
Back to India
In mid-November, we’ll make another trip to India. This trip will include:
Key leaders from DBT, Missy and AO
Care and feeding of the team through the transition.
Building toward the future with our ways of working and staffing.
Source: All Hands slide 36

## Slide 37: DGS Leadership Transition: Update
OPS PRIORITIES
Owner(s)
[Names]
What has been accomplished
[Put here: what got done since last time. Use dates, not "recently". Why: shows real progress.]
Next milestones
[Put here: what happens next, and by when. Why: people can hold us to it.]
What is in our way / what we need from you
[Put here: what is blocking us, and what we need from you. Say who, and by when. Why: this is how leaders can help.]

## Slide 38: Intake Updates
CRITICAL ENABLERS
Owner(s)
Missy Foristall, McComas, Deana, John E.
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 39: Intake Updates: Context
CRITICAL ENABLERS
Owner(s)
Missy Foristall, McComas, Deana, John E.
KEY TAKEAWAY
Upstream of Delivery Models: how a request even reaches the right people before it becomes a deal.
2026 GOAL
[Enter 2026 goal, and what it means in practice]
THE PROBLEM
Adoption has been slow: people still go to known individuals for help, cutting into BU visibility and our ability to help.
C&C has been informed of the alias and process.
WHAT WE ARE CHANGING
DDM_Opportunity and DBT_Opportunity are live, so requests reach the right BU SMEs without needing to know a matrix of names.
Requests are reviewed and assigned to a lead within the BU. The lead gathers more info, pulls in solutioning support, and makes sure the request is handled: creds, calls, PT entry.
SME Case Request in SF (10/16 target): covers deals under $500K, small ad-hoc projects, multi-person sprints, exec meetings, and case studies.
RACI updates (11/1 estimated): clarify roles for everyone in intake.
WHAT THIS UNLOCKS
Requests get emailed to the right alias and land in a list for easy review and follow-up.
SME expertise comes in earlier, before the deal is shaped, which can lift our win rate on the deal volume we already capture.
Beyond the MVP
[Enter what this makes possible next]
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 40: Why now
INTAKE UPDATES · CLICK-DOWN · THE PROBLEM
Owner(s)
Missy Foristall, McComas, Deana, John E.
[Put here: one or two sentences on why this one, and why now. What does waiting cost us?]
What's happening today
[Put here: what is going on right now that makes this urgent. One bullet per point, add as many as you need.]
[Why: this is the reason to act now.]
So we need
[Put here: what has to happen or be decided. One bullet per ask.]
[Why: this turns the worry into a clear ask.]

## Slide 41: How we're going about it
INTAKE UPDATES · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
Missy Foristall, McComas, Deana, John E.
What's behind the alias
Request is reviewed and assigned to a lead within the BU
Lead reaches out to gather more info, pulls in solutioning support, and ensures the request is handled — creds, calls, PT entry, etc.
Step 1
Alias Creation
DDM_Opportunity@merkle.com and DBT_Opportunity@merkle.com are live, so requests reach the right BU SMEs without needing to know a matrix of names.
Step 2
Adoption
C&C has been informed of the alias and process
Adoption has been slow: People still go to known individuals for help, cutting into BU visibility and ability to help
Step 3
Leadership Ask
C&C leadership support in redirecting request
Step 4
SME Case Request in SF
Updating the existing tool to cover more scenarios:
New pursuit or deals under $500k
Ad-hoc client request for a small new project
Sprints involving multiple people
Client exec-level meetings needing decks and materials
Case studies, capability decks, etc.
Step 5
RACI Updates
Underway, to clearly articulate roles and responsibilities for everyone involved in the intake process.
10/16 target launch date
SME Case Request in SF
Requests get emailed to the right alias AND land in a list for easy review and follow-up.
11/1 Estimated Rollout
RACI Updates
The target
MVP done
[Date we are shooting for.]
Team
[Who does the work]
[Who does the work]
Partners
[Who we work with]
[Who we work with]
Source: All Hands slide 38 · Delivery Excellence slide 17

## Slide 42: The stories
INTAKE UPDATES · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
Missy Foristall, McComas, Deana, John E.
Story
How we measure success
Status
The stories
1
Alias Creation
[How will we know it worked? A number or a clear yes or no.]
[Status]
2
Adoption
[How will we know it worked? A number or a clear yes or no.]
[Status]
3
Leadership Ask
[How will we know it worked? A number or a clear yes or no.]
[Status]
4
SME Case Request in SF
[How will we know it worked? A number or a clear yes or no.]
[Status]
5
RACI Updates
[How will we know it worked? A number or a clear yes or no.]
[Status]
Source: All Hands slide 38 · Delivery Excellence slide 17

## Slide 43: Intake Updates: Update
CRITICAL ENABLERS
Owner(s)
Missy Foristall, McComas, Deana, John E.
WHAT HAS BEEN ACCOMPLISHED
Alias creation complete: DDM_Opportunity and DBT_Opportunity are live.
C&C has been informed of the alias and process.
NEXT MILESTONES
SME Case Request in SF: 10/16 target launch date.
RACI updates: 11/1 estimated rollout.
WHAT IS IN OUR WAY / WHAT WE NEED FROM YOU
Adoption has been slow: people still go to known individuals for help, cutting into BU visibility and ability to help.
Leadership ask: C&C leadership support in redirecting request.
Notes: ⚠️ DESIGNER REVIEW: Custom layout — verify fit and spacing.

## Slide 44: Ops Transformation: Rebuild Scoping & Staffing
OPS PRIORITIES
Owner(s)
[Names]

## Slide 45: Ops Transformation: Rebuild Scoping & Staffing
OPS PRIORITIES · EXEC SUMMARY
Owner(s)
[Names]
2026 Goal
[Put here: the one thing we want to be true by the end of 2026.]
[Why: everyone should know the finish line.]
The problem
[Put here: what is broken today, in plain words.]
[Why: people only back a fix if they can feel the problem.]
What we are changing
[Put here: what we will do differently. Use short bullets.]
[Why: it shows we have a plan, not just a worry.]
What this unlocks
[Put here: what gets better once this works.]
[Why: it is the reason the effort is worth it.]
Key takeaway
Deliverables go in, and a timeline and staffing plan come out. AI does the real work of generating the plan, and gets smarter from what we actually deliver.
Source: Delivery Excellence kickoff slide 19

## Slide 46: Why now
OPS TRANSFORMATION: REBUILD SCOPING & STAFFING · CLICK-DOWN · THE PROBLEM
Owner(s)
[Names]
[Put here: one or two sentences on why this one, and why now. What does waiting cost us?]
What's happening today
[Put here: what is going on right now that makes this urgent. One bullet per point, add as many as you need.]
[Why: this is the reason to act now.]
So we need
[Put here: what has to happen or be decided. One bullet per ask.]
[Why: this turns the worry into a clear ask.]

## Slide 47: How we're going about it
OPS TRANSFORMATION: REBUILD SCOPING & STAFFING · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
This is a new ask, and we are still working through it. More to come.
Step 1
Goes In
Deliverables
Step 2
Ai Does The Real Work
Generating the plan
Step 3
Comes Out
Timeline + staffing plan
[Date]
[What is done by then]
[Date]
[What is done by then]
[Date]
[What is done by then]
[Date]
[What is done by then]
The target
MVP done
[Date we are shooting for.]
Team
[Who does the work]
[Who does the work]
Partners
[Who we work with]
[Who we work with]
Source: Delivery Excellence kickoff slide 19

## Slide 48: The stories
OPS TRANSFORMATION: REBUILD SCOPING & STAFFING · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
Story
How we measure success
Status
The MVP
1
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
2
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
3
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
After the MVP
4
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
5
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]

## Slide 49: Ops Transformation: Rebuild Scoping & Staffing: Update
OPS PRIORITIES
Owner(s)
[Names]
What has been accomplished
[Put here: what got done since last time. Use dates, not "recently". Why: shows real progress.]
Next milestones
[Put here: what happens next, and by when. Why: people can hold us to it.]
What is in our way / what we need from you
[Put here: what is blocking us, and what we need from you. Say who, and by when. Why: this is how leaders can help.]

## Slide 50: Earlier Delivery & Talent in Pursuits
OPS PRIORITIES
Owner(s)
[Names]

## Slide 51: Earlier Delivery & Talent in Pursuits
OPS PRIORITIES · EXEC SUMMARY
Owner(s)
[Names]
2026 Goal
[Put here: the one thing we want to be true by the end of 2026.]
[Why: everyone should know the finish line.]
The problem
[Put here: what is broken today, in plain words.]
[Why: people only back a fix if they can feel the problem.]
What we are changing
[Put here: what we will do differently. Use short bullets.]
[Why: it shows we have a plan, not just a worry.]
What this unlocks
[Put here: what gets better once this works.]
[Why: it is the reason the effort is worth it.]
Key takeaway
Without clear roles tied to supporting pitch and pursuit, we continue to pull delivery resources that are fully allocated into conversations that they can't give the appropriate attention to. This will continue to be a problem until we get the right skillsets with the right availability identified and in place.
Source: All Hands slide 40 · Delivery Excellence slide 21

## Slide 52: Why now
EARLIER DELIVERY & TALENT IN PURSUITS · CLICK-DOWN · THE PROBLEM
Owner(s)
[Names]
Why this one, now: By bringing SME expertise into upfront deal evaluation, we can increase our win rate on the deal volume we're already capturing. Quick execution is essential to drive Q4 and 2027 revenue.
What's happening today
[Put here: what is going on right now that makes this urgent. One bullet per point, add as many as you need.]
[Why: this is the reason to act now.]
So we need
[Put here: what has to happen or be decided. One bullet per ask.]
[Why: this turns the worry into a clear ask.]
Source: All Hands slide 40 · Delivery Excellence slide 21

## Slide 53: How we're going about it
EARLIER DELIVERY & TALENT IN PURSUITS · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
[Put here: one line on how we are tackling this. The steps below fill in the detail.]
Step 1
PHASE 1 · Planning and Discovery: Now – 10/30
Define Roles Needed
Determine the specific roles need for pursuit support (alliance partner, skillset) along with allocations, roles and responsibilities
Clarify if Internal or External Moves
Review existing team roster to see who can move to these new roles and where we need to hire
Update Existing Org Structure
Update the existing org structure (as needed) to best support these roles and the pursuits
Step 2
PHASE 2 · Execution on Changes: 11/2 – 12/24
Open Reqs
Once aligned on the needs, prioritize needs and open reqs for the first set of new roles (or for backfills, if moving existing people into the new roles)
Create Transition Plan
Identify any accounts that need to move to allow people to switch to a new role and create a 30/60 day transition plan
Now – 10/30
Planning and Discovery
11/2 – 12/24
Execution on Changes
The target
MVP done
[Date we are shooting for.]
Team
[Who does the work]
[Who does the work]
Partners
[Who we work with]
[Who we work with]
Source: All Hands slide 40 · Delivery Excellence slide 21

## Slide 54: The stories
EARLIER DELIVERY & TALENT IN PURSUITS · CLICK-DOWN · WHAT WE ARE CHANGING
Owner(s)
[Names]
Story
How we measure success
Status
The MVP
1
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
2
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
3
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
After the MVP
4
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]
5
[Short story name]
[A few words on what it is. Optional.]
[How will we know it worked? A number or a clear yes or no.]
[Status]

## Slide 55: Earlier Delivery & Talent in Pursuits: Update
OPS PRIORITIES
Owner(s)
[Names]
What has been accomplished
[Put here: what got done since last time. Use dates, not "recently". Why: shows real progress.]
Next milestones
[Put here: what happens next, and by when. Why: people can hold us to it.]
What is in our way / what we need from you
[Put here: what is blocking us, and what we need from you. Say who, and by when. Why: this is how leaders can help.]

## Slide 56: [Add a header]
LAYOUT 1 · COLUMNS · TEMPLATE · SUPPORTING DETAIL
[Add a header]
[Use when there are 2 to 4 things side by side, like options, models or examples. Give each a name, a line on what it is, and a few key points.]
[Add a header]
[Use when there are 2 to 4 things side by side, like options, models or examples. Give each a name, a line on what it is, and a few key points.]
[Add a header]
[Use when there are 2 to 4 things side by side, like options, models or examples. Give each a name, a line on what it is, and a few key points.]
[Add a header]
[Use when there are 2 to 4 things side by side, like options, models or examples. Give each a name, a line on what it is, and a few key points.]

## Slide 57: [Add a header]
LAYOUT 2 · PHASES AND DATES · TEMPLATE · SUPPORTING DETAIL
Phase 1 · [Name] · [Dates]
[Milestone, if there is one.]
[Step]
[What happens, in plain words.]
[Step]
[What happens, in plain words.]
[Step]
[What happens, in plain words.]
Phase 2 · [Name] · [Dates]
[Milestone, if there is one.]
[Step]
[What happens, in plain words.]
[Step]
[What happens, in plain words.]
[Step]
[What happens, in plain words.]

## Slide 58: [Add a header]
LAYOUT 3 · STATEMENT AND POINTS · SUPPORTING DETAIL
[One statement: the thing to take away.]
[Point]
[Supporting detail.]
[Point]
[Supporting detail.]
[Point]
[Supporting detail.]
[Optional: one closing line.]

## Slide 59: [Add a header]
LAYOUT 4 · FLOW · TEMPLATE · SUPPORTING DETAIL
[One line on what the flow shows.]
[Goes in]
[…]
[What happens]
[…]
[Comes out]
[…]
[Optional: a closing line, a status, or a caveat.]