## Slide 1: Earlier delivery and talent involvement in major pursuits
EARLIER DELIVERY & TALENT IN PURSUITS · DETAIL · DDM QUICK WIN EXAMPLE
Owner(s)
Missy Foristall, Deana Derocha
By bringing SME expertise into upfront deal evaluation, we can increase our win rate on the deal volume we're already capturing. Quick execution is essential to drive Q4 and 2027 revenue.
PHASE 1
Planning and Discovery: Now – 10/30
PHASE 2
Execution on Changes: 11/2 – 12/24
Define Roles Needed
Determine the specific roles need for pursuit support (alliance partner, skillset) along with allocations, roles and responsibilities
Clarify if Internal or External Moves
Review existing team roster to see who can move to these new roles and where we need to hire
Update Existing Org Structure
Update the existing org structure (as needed) to best support these roles and the pursuits
Open Reqs
Once aligned on the needs, prioritize needs and open reqs for the first set of new roles (or for backfills, if moving existing people into the new roles)
Create Transition Plan
Identify any accounts that need to move to allow people to switch to a new role and create a 30/60 day transition plan
Key takeaway
Without clear roles tied to supporting pitch and pursuit, we continue to pull delivery resources that are fully allocated into conversations that they can't give the appropriate attention to. This will continue to be a problem until we get the right skillsets with the right availability identified and in place.