## Slide 1: DGS Leadership Transition
DGS LEADERSHIP TRANSITION · DETAIL
Owner(s)
Missy Foristall, Adam Organ
Naazneen's departure on 12/31 is a fixed deadline, and her role covers more ground than any one market realizes — global delivery, market relationships, capability development, and financial oversight. This is a two-phase effort to capture what she knows and put durable ownership in place before she leaves.
PHASE 1
Intake, Validate, Plan · Sept 14 – Oct 16
Milestone: India trip Sept 25 – Oct 10 (AO)
PHASE 2
Align, Anchor, Execute · Oct 19 – Dec 20
Milestone: India trip mid-Nov (AO, Missy, Eric, McComas)
Role & Org Mapping
Sessions with Naazneen's team to document formal and informal responsibilities, relationships, and escalation paths.
Coverage & Role Design
Determine who — and # of people — are needed to take on what Naazneen has been doing. Separate the DBT-specific work from the broader set of responsibilities she carries.
Alignment Prep
Establish scope, decision rights, and messaging ahead of wider stakeholder engagement.
Operating Model Decisions
Finalize market vs. India ownership of delivery escalation, solutioning participation, and shared governance.
Leadership & Talent Plan
Confirm critical role coverage, succession, recruiting priorities, and capability gaps.
Execution & Handoff
Complete transition activities and communications ahead of the 12/31 departure.
Extentia's Organic Revenue: Multi-market structure (US, ANZ, India, UK) and P&L ownership need to be resolved for 2027 — likely a longer runway than the core transition timeline. Tracking separately so it doesn't block Phase 1 & 2 progress.
Key takeaway
We have a hard deadline and a business with real complexity underneath it. This two-phase plan is how we capture the knowledge, resolve ownership, and land a clean transition by year-end.